## Sheet1
2009-09-11 | Signed petitions submitted to Hamburg Township
2009-11-05 | Township Board resolution #1 for reimbursement
2009-12-01 | Township Board resolution #2 for plans and cost estimates
2009-12-15 | Township Board resolution #3 for first hearing and statutory notices
2010-02-03 | Notices of First Hearing sent via postal mail and published in newspaper
2010-02-15 | Hold First Public Hearing
2010-02-16 | Township Board resolution #4 for petitions, approval of project, cost estimates, S.A.D. creation and preparation of S.A.D. roll
2010-03-16 | Township Board resolution #5 for Second Hearing and statutory notices
April 6-13, 2010 | Notices of Second Public Hearing sent via postal mail and published in newspaper
2010-04-20 | Hold Second Public Hearing
2010-04-20 | Township Board resolution #6 confirms the S.A.D. roll
2010-04-20 | Township Board resolution #7 authorizing the Bond
2010-05-20 | Expiration of 30-day Period to Challenge Special Assessments
2010-07-01 | Begin Construction and Road Re-Paving project
August/September 2010 | Construction Completed on Road Improvement Project
2010-09-30 | Significant restoration completed including grass seeding of all disturbed areas
2010-12-01 | First Special Assessment installment is included on the December tax bill